Table 3. FTE revisited for sep 2007- dec 2008 COSMO year

the activities for 2007-2008 COSMO year are in BOLD

| Task | FTE/year | Start (or continue) | Milestones | End |
| --- | --- | --- | --- | --- |
| - Delivery of CVS software | 0.2 (WG coordinator) 0.14 (members) | mid Sep | WG5 Wshop and delivery of the package and user manual | Completed |
| - DB | 0,5 | Sep 2006 | Complete DB Architecture | Mar 2007 completed |
| - Selection | 0,2 | Jan 2006 | Identification of CV variables | Apr 2006 (completed) |
| - Load | 0,6 | Apr 2007 | SW to load data in DB ready | Dec 2007 (delayed) |
| - Filters 1 (meta-tool) | 0.1 | Early 2006 | Delivery of meta-tool SW | Oct 2006 Completed |
| - Filters 2 | 0.5 | Aug 2007 | Delivery of filters SQL lang. | Jan 2008 |
| - Porting CVS 6.a functionalities test and comparison | 0.5 (increased) | Delayed Nov 2007 for 6a | Integration of 2 packages, use of “R” as statistical package | Mar/Apr 2008 for 6a |
| 6.b implementation graphic package | 0.6 | Aug 2007 for 6b | standard graphic package for CVS | Completed 6b (user manual and delivery expected) |
| - Test | 0.25 (decreased) | Mar/Apr 2008 | Comparing products/scores/input files | May 2008 |
| - Delivery of package | 0.3 | May 2008 | Package ready for use | Aug 2008 |
| - Delivery of library | 0.2 (plus 0,02 for any member) | Aug 2008 | Library ready and workshop/course | Oct-Nov 2008 |

GREEN = Completed  YELLOW= ongoing RED =Delayed WHITE =from 2008