Project outline: Common Conditional Verification (CV) package and library

Extended Status report September 2007

List of people involved in the project: Adriano Raspanti (project leader), Angela Celozzi, (CNMCA), Rodica Dumitrache, Aura Lupascu (NMA).

Aim:	Development of a common and unified verification “library” including a Conditional Verification tool. This library will be included in the public COSMO SW. The development of a already complete Conditional Verification Tool will be the first priority and outcome of this project (see Summary of the joint WG3-5 workshop held on 09/03/2005 in Langen)

.

Motivation:	The main purpose of CV is the systematic evaluation of model performances in order to reveal, in a way different from the usual classical verification tools. Once delivered and applied routinely, it should provide information straight  to the WG[1-3] scientists to provide them hints which could be the causes of model deficiencies that can be seen in the operational verification. When completed It should be easily possible to turn out a common and unified verification library, useful for all COSMO community for operational and research points of view.

.

Method:	The typical approach to CV could consist of the selection of one or several forecast products and one or several mask variables or conditions, which would be used to define thresholds for the product verification (e.g. verification of T2M only for grid points with zero cloud cover in model and observations). After the selection of the desired conditions, a classical verification tools to turn out statistical indexes can be used.

The more flexible way to perform a selection of forecasts and observations following a certain number of conditions, is to use an “ad hoc database”, planned and designed for this purpose, where the mask or filter could be simply or complex SQL statements.

Prerequisites and/or link with other activities:	Delivery of the Common verification suite (working package 5.6.1), which will be available after the end of its test phase (almost done).

Project leader:	Adriano Raspanti (CNMCA)

Possible criticity:

- Lack of FTE’s resources from some countries delayed the development of the project;

- Implementation of verification procedures for non-GTS data (e.g. standard input format BUFR code for DB)

Description of Tasks (in order of delivery) and work done for 2006-2007 COSMO year - Revisited (aug 2007):

- Database design and implementation (DB): study of the ECMWF ODB to understand if it can be used as a working DB at least for the LM reference version running at the ECMWF; if not an ‘ad hoc’ database has to designed and implemented;

- Work done: study of ODB is still in progress, but only for a possible implementation at ECMWF for the LM reference version; for the package an “ad hoc” database structure has been studied and implemented, but not fully realised yet, on the basis of CNMCA operational DB. A free commercial DB will be implemented to complete this task (MYSQL). The study and design phases are completed and a detailed project is ready for the implementation. This will start as soon as possible carried out by external personnel, with an “ad hoc” contract. (WORK started 27 august)

- First selection of observation and forecasts data to handle with (Selection);

- Work done: the selection is completed on the basis of the following table

| Verified variable | Mask variable(s) | Criteria | Remarks |
| --- | --- | --- | --- |
| T2m | CLC(t); local time | lower & upper thresholds in CLC; local time slots | cloud cover thresholds should be applied over the time period preceding the verification time and both to model and observations |
| T2m | Wsoil | lower & upper thresholds in (relative to field capacity) soil moisture | soil moisture is a multi-layer variable and it may be useful to compute an ‚effective‘ soil moisture as average over several layers |
| T2m | SHF/LHF | thresholds in Bowen ratio | Bowen ratio as an indirect measure of soil wetness needs to be considered as an average over time |
| CLC(L) | vertical stability index | ‚stable‘ versus unstable situations | differences in temperatures at various pressure levels may be used as a stability index; the distinction with regard to stability may be considered as an example for situation dependent masking, e.g. to focus on low level stratus or convective regimes |
| RR | as above | as above | regime dependent precipitation verification |
| U10m | z0 | low, medium, large z0 | correlation between wind speed errors and roughness length may point to problems in external parameters |
| T2m | U10m | upper threshold in wind speed | exclude advection dominated situations in temperature verification |
| Td2m | Wsoil | lower & upper thresholds in (relative to field capacity) soil moisture | determine the error of dew point temperatures in the case of dry soils versus wet soils |
| T2m | Wsnow | No snow/ broken snow/ snow | The temperature error is likely to depend on snow cover yes/no, a broken snow deck might be an indicator for melting snow |

Of course further implementations, suggestions and upgradings are possible and welcome.

- Implementation of procedure to load  data into database (simpler version): data will be loaded not in binary form, but in decoded form both for observation and forecast (time series interpolated on observation location);

Work done:  almost completed. To be implemented algorithms to perform mean and upscaling of data for various parameters (cloudiness, precipitation). To be complete the implementation of FC and OBS tables.

- Creation of a number of guide filters/masks to retrieve data conditionally (Filters 1 and 2) - see [1], for a set o possible conditions/masks and for general suggestions, and [3]. As a first output a ‘meta-tool’ could be created just to begin to perform some simple conditional verification, while awaiting for the complete package (see specification from [3]); this using an extended version of Common Verification Suite package, in order to start as soon as possible with CV of operational model suites (at least for the reference version).

- Work done:  tests masks/filters above have been implemented and are now under test at CNMCA connected with Common Verification Suite (T2m with clouds and wind, e.g.)..

- Development of the final filters/mask in SQL language. This can be seen as priority 1 of the project: Work started in august 2007 and delayed until jan 2008.

- Porting and merging of Common Verification Suite package to perform statistics (Porting CVS WP 5.6.1);

  - Functionalities test of the new package for conditional verification with a gross comparison of the results obtained with the old package (with no condition and using the meta-tools implemented until now) and the new one. (to be postponed start Nov 2007)

  - Development and implementation of a “standard” graphic package to be implemented on the basis of the Scores ascii file carried out by the CVS package. This package should be based on a freeware or shareware software (e.g. “R”, gnuplot, Grace) and allow the presentation of the usual statistical scores alone or overlaying two of more of them (e.g POD and POD/FAR). (completed the first implementation, interesting results to be extended). User guide will be provided for the use of the package (not planned before)

- Test phase of early results (Test): statistics and graphs distibuted to users (WG3 and WG5 people mainly) for studies, suggestions ...

- Delivery of the complete package (Delivery CV), as priority 2.

- Delivery of the common library for verification (to be outlined).

Note: A Special Task 0 has been added for the delivery of CVS package (see task 0 table 2 - 2007 Version): COMPLETED

See table 1 and table 2 for old FTE planned, and table 3 for a new version of FTE’s (to be approved)

Table 1. FTE planned for 2006

| Task | Suggested Scientist (opt) | FTE/year | Start | Milestones | End |
| --- | --- | --- | --- | --- | --- |
| DB |  | 1 | Jan 2006 | Complete DB Architecture | Jun 2006 |
| Selection | UGM post-graduate 0.2 - …. | 0.5 | Jan 2006 | Identification of CV variables | Apr 2006 |
| Load/ret |  | 1.2 | Jun 2006 | Delivery of SW | Dec 2006 |
| Filters 1 (meta-tool) | Raspanti 0.2 - UGM Post-graduate 0.2 | 0.4 | Early 2006 | Delivery of meta-tool SW | Aug 2006 |
| Filters 2 | Raspanti 0.05 | 0.8 | Jan 2007 | Delivery of filters SW | Jul 2007 |
| Porting CVS | Galliani 0.5 - … | 1 | Aug 2007 | Integration of 2 packages | Dec 2007 |
| Test | Galliani 0.1 | 0.5 | Jan 2008 | Comparing products/scores | May 2008 |
| Delivery of package |  | 0.1 | Jan 2008 | Package ready for use | May 2008 |
| Delivery of library |  | 0.1 | May 2008 | Library ready | Jun 2008 |

To overcome problems connected with the lack of FTEs criticity and in order to maintain almost the same planned deadlines an FTEs decreasing has been adopted (based on this year experiences), as in table 2.

Also required resources for 2007 and for full period have been changed accordingly.

Required Resources:

- required for 2007: 2 FTE

- required in total: planned 5.5  FTE (end 2008), reduced to 4,34 FTE (total of 2006 actually done plus estimated for 2007-2008 and new Task 0)

Table 2. FTE revisited for sep 2006- sep 2007

| Task | FTE/year | Start (or continue) | Milestones | End |
| --- | --- | --- | --- | --- |
| Delivery of CVS software | 0.2 (WG coordinator) 0.14 (members) | mid Sep | WG5 Wshop and delivery of the package and user manual | Completed |
| DB | 0,5 | Sep 2006 | Complete DB Architecture | Mar 2007 Almost completed |
| Selection | 0,2 | Jan 2006 | Identification of CV variables | Apr 2006 (completed) |
| Load | 0,6 | Apr 2007 | Delivery of SW | Dec 2007 (delayed) |
| Filters 1 (meta-tool) | 0.1 | Early 2006 | Delivery of meta-tool SW | Oct 2006 Completed |
| Filters 2 | 0.6 | Aug 2007 | Delivery of filters SQL lang. | Jan 2008 |
| Porting CVS 6.a functionalities test and comparison 6.b implementation graphic package | 0.9 | Aug 2007 (for 6b) | Integration of 2 packages and standard graphic package | Dec 2007 Completed 6b |
| Test | 0.3 | Jan 2008 | Comparing products/scores | May 2008 |
| Delivery of package | 0.2 | Jan 2008 | Package ready for use | May 2008 |
| Delivery of library | 0.2 | May 2008 | Library ready | Jul 2008 |

Description of Tasks (in order of delivery) and work to be done for 2007-2008 COSMO year - Revisited September 2007

To avoid confusion with the CVS Working package, the project could renamed VERSUS (Verification System Unified Survey)

- TASK 5: Development of the final filters/mask in SQL language. Work started in august 2007 and delayed until jan 2008: Web-based user interface will be delivered to perform statistics. Three levels of users will be defined: administrator, primary user, secondary user. The primary user will be able to load his own data (following technical specifications if standard inputs) and to perform his own statistics (with graphics), while the secondary will have access to the already existing statistics. (FTE 0,6) In parallel with this task also TASK 3 (loader) will be concluded (FTE 0,1).

- TASK 6a: Porting and merging of Common Verification Suite package to perform statistics: this package has been updated and changed. The porting will be performed only from functional point of view; statistics will be performed through the use of “R” package. “R” package will be linked (already done) with the MySQL DB developed “ad hoc” for verification purposes. Work will (postponed) start nov 2007 and end for mar 2008. Due to this change, higher FTE needs, from 0.3 to 0,5. Functionalities test of the new package for conditional/no conditional verifications with a comparison of the results obtained with the old package will be performed.

- TASK 7: Test phase: will be performed with the support of any member of COSMO community. Grib and BUFR files will be collected by the project leader team and used to perform verifications with the new package. The results will be discussed and compare before the actual delivery of the package. FTE: 0,15 for project leader team and a total of 0,10 FTE for the remaining COSMO community (data packaging and distribution and comparison of the independent results).

- TASK 8: Preparation of the VERSUS package for delivery (hopefully a “plug&play installation”) and the User manual. FTE: 0,4 (at least tested on other two different Linux OS)

- TASK 9: Delivery of the common library for verification: an “ad hoc” workshop will be organise for the delivery of the package, as in nov 2006 for CVS package. During this workshop Software package and User manual will be officially delivered; the main functionalities will be shown and a short course for installation and “first” use of the package will be held. FTE: 0,2 for Project leader and 0,02 for any participant from any member of COSMO community.

Required Resources:

- required for 2007-2008 COSMO year: 2 FTE

- required in total: planned 5.5  FTE (end 2008), reduced to 4,34 FTE (total of 2006 actually done plus estimated for 2007-2008 and new Task 0) in 2007. Total planned for the end of the Project in 2008 FTE 4,7

Table 3. FTE revisited for sep 2007- dec 2008 COSMO year

the activities for 2007-2008 COSMO year are in BOLD

| Task | FTE/year | Start (or continue) | Milestones | End |
| --- | --- | --- | --- | --- |
| Delivery of CVS software | 0.2 (WG coordinator) 0.14 (members) | mid Sep | WG5 Wshop and delivery of the package and user manual | Completed |
| DB | 0,5 | Sep 2006 | Complete DB Architecture | Mar 2007 completed |
| Selection | 0,2 | Jan 2006 | Identification of CV variables | Apr 2006 (completed) |
| Load | 0,6 | Apr 2007 | SW to load data in DB ready | Dec 2007 (delayed) |
| Filters 1 (meta-tool) | 0.1 | Early 2006 | Delivery of meta-tool SW | Oct 2006 Completed |
| Filters 2 | 0.5 | Aug 2007 | Delivery of filters SQL lang. | Jan 2008 |
| Porting CVS 6.a functionalities test and comparison | 0.5 (increased) | Delayed Nov 2007 for 6a | Integration of 2 packages, use of “R” as statistical package | Mar/Apr 2008 for 6a |
| 6.b implementation graphic package | 0.6 | Aug 2007 for 6b | standard graphic package for CVS | Completed 6b (user manual and delivery expected) |
| Test | 0.25 (decreased) | Mar/Apr 2008 | Comparing products/scores/input files | May 2008 |
| Delivery of package | 0.3 | May 2008 | Package ready for use | Aug 2008 |
| Delivery of library | 0.2 (plus 0,02 for any member) | Aug 2008 | Library ready and workshop/course | Oct-Nov 2008 |

GREEN = Completed  YELLOW= ongoing RED =Delayed WHITE =from 2008

References (annexes)

- [1] “CV of NWP forecast product”,  Heise, Ritter - April 2005 DWD;

- [2] “Summary of the joint WG3-5 workshop held on 09/03/2005 in Langen”, Emiliani April 2005;

- [3] Summary of the discussions at the joint COSMO WG3-WG5 workshop, 9.3.2005, Langen, Arpagaus - April 2005.