## Slide 1: COTEKINO Priority Project
COSMO WG7
Chiara Marsigli

## Slide 2: COTEKINO Priority Project
Duration: 2 years, 2013-2015
FTEs: 5 (3 FTEs 2013/2014 and 2 FTE 2014/2015)
Aim: develop and test perturbation methodologies for the convection-permitting ensembles
Involved COSMO partners: Italy, Switzerland, Poland, Russia and Germany
PP tasks:
  IC peturbations from KENDA
  Model perturbations:
    SPPT
    SKEB
    stochastic physics
  Lower boundary perturbations

## Slide 3: Task 1. IC perturbations derived from KENDA
1.1 Communication about experiments and results. Exchange of dedicated tools. (0.55 FTEs)
  Chiara Marsigli (ARPA-SIMC), André Walser (MCH), Richard Keane (DWD) - 01.09.2013 - 31.08.2015
  Deliverable : meetings, in person at the GM and CUS and by web-conference (minutes).
1.2 Coordination with the KENDA PP (0.2 FTEs)
  Chiara Marsigli (ARPA-SIMC), Daniel Leuenberger (MCH) - 01.09.2013 - 31.08.2015
  Deliverable: meetings and email exchange. Reports on the advancement of the tests, exchange of tools.

## Slide 4: Task 2. Model perturbations
2.1 Test SPPT at 2.2/2.8 km (1.3 FTEs)
  2.1.1 ARPA-SIMC/CNMCA: Analyse the impact w. r. t. perturbed parameters and deterministic verification of perturbed members
  2.1.2 MCH: Analyse the impact with respect to a non perturbed ensemble and further develop the scheme
  2.1.3 RHM: Test of SPPT in the Sochi 2.2 ensemble to assess the effect w.r.t the current method.
  Chiara Marsigli (ARPA-SIMC), Lucio Torrisi (CNMCA), Marco Arpagaus and Daliah Maurer (MCH), Elena Astakhova and Dmitry Alferov (RHM) - 01.09.2013 - 31.03.2015
  Deliverable: Definition of an optimal set-up of the SPPT scheme for perturbing the COSMO model at 2.2/2.8km (report).

## Slide 5: Task 2. Model perturbations
2.2 Test SKEB at 2.2 km (0.3 FTEs)
  Marco Arpagaus (MCH) – 01.10.2013 – 31.05.2014
  Deliverable: Assessment of the performance (report).
2.3 Link with the development of a new model perturbation strategy at DWD (0.25 FTEs)
  Ekaterina Machulskaya and Richard Keane (DWD), 01.09.2013 - 31.08.2015
  Deliverable: email exchange, 2 meetings per year at DWD (coordination with task 1)

## Slide 6: Task 3. Lower boundary perturbations
3.1 Study of COSMO model sensitivity to lower boundary initial conditions (0.7 FTEs)
  Nicola Loglisci and Riccardo Bonanno (ARPA Piemonte), Andrzej Mazur and Grzegorz Duniec (IMGW) 01.09.2013 - 31.01.2014
  Deliverable: Sensitivity tests of COSMO to different lower boundary initial conditions (report).
3.2 Scientific analysis of possible strategies: literature review, assessment of suitable methods (0.3 FTEs)
  Nicola Loglisci and Riccardo Bonanno (ARPA Piemonte), Andrzej Mazur and Grzegorz Duniec (IMGW), Inna Rozinkina and Gdaly Rivin (RHM), 01.09.2013 - 31.03.2014
  Deliverable: Definition of one or more techniques for lower boundary perturbations to be developed for COSMO (report).

## Slide 7: Task 3. Lower boundary perturbations
3.3 Develop techniques for lower boundary perturbation (1.4 FTEs)
  3.2.1 test of perturbation of soil model parameters (RHM)
  3.2.2 selection and preparation of algorithms
  3.2.3 setting a test-bed, implementation and testing
  3.2.4 analyse the impact with respect to a non perturbed ensemble
  Nicola Loglisci and Riccardo Bonanno (ARPA Piemonte), Andrzej Mazur, Witold Interewicz and Grzegorz Duniec (IMGW), Inna Rozinkina and Gdaly Rivin (RHM), 28.03.2014 - 31.08.2015
  Deliverable: Algorithm(s) for lower boundary perturbation implemented in one or more ensemble systems for testing.

## Slide 8: First planned actions
Task 1: meeting on ICs perturbation (with KENDA); planned exchange of tools
Task 2: meeting on physics perturbations (visit of G. Shutts to DWD)
Task 2.1: work on SPPT going on at MCH
Task 2.2: implementation of SKEB in COSMO (MCH, visit of J. Berner in September)
Task 3: Definition of sensitivity experiment for lower boundary perturbations (SON 2013); literature review