## Slide 1: COTEKINO Priority Project
COSMO WG7
Chiara Marsigli

## Slide 2: COTEKINO PP
PP duration: tentatively 2 years, 2013-2015
Aim: develop and test perturbation methodologies for the convection-permitting ensembles
CP ens:
  DWD: operational
  MeteoSwiss and Italy: under development
  Russia: implemented for Sochi Olympics
  Poland: planned
PP tasks:
  IC peturbations from KENDA (only coordination)
  Model perturbations:
    SPPT
    SKEB
    Coordination with DWD for new physics perturbation
  Soil/surface perturbations

## Slide 3: Task 1. IC perturbations derived from KENDA
1.1 Communication about experiments and results. Exchange of dedicated tools. (0.55 FTEs)
  Chiara Marsigli (ARPA-SIMC), André Walser (MCH), Richard Keane (DWD) - 01.09.2013 - 31.08.2015
  Deliverable : meetings between scientists working on this issue, in person at the GM and CUS and at least twice per year by web-conference (minutes).
1.2 Coordination with the KENDA PP (0.2 FTEs)
  Chiara Marsigli (ARPA-SIMC), Daniel Leuenberger (MCH) - 01.09.2013 - 31.08.2015
  Deliverable: Participation to the KENDA meetings and email exchange. Documentation of techniques to derive IC perturbations from KENDA, and related tools.

## Slide 4: Task 2. Model perturbations.
2.1 Test SPPT at 2.2/2.8 km (1.3 FTEs)
  2.1.1 ARPA-SIMC/CNMCA: Analyse the impact w. r. t. perturbed parameters and deterministic verification of perturbed members.
  2.1.2 MCH: Analyse the impact with respect to a non perturbed ensemble and further develop the scheme.
  2.1.3 RHM: Overview the available methods for model perturbations. Test of SPPT in the Sochi 2.2 ensemble to assess the effect w.r.t the current method.
  Chiara Marsigli (ARPA-SIMC), Lucio Torrisi (CNMCA), Marco Arpagaus (MCH) and Daliah Maurer (MCH), Elena Astakhova and Dmitry Alferov (RHM) - 01.09.2013 - 31.03.2015
  Deliverable: Definition of an optimal set-up of an advanced SPPT scheme for perturbing the COSMO model at 2.2/2.8km.
2.2 Test SKEB at 2.2 km (0.3 FTEs)
  Marco Arpagaus (MCH)
  Deliverable: Assessment of the performance. (report)

## Slide 5: Task 2. Model perturbations.
2.3 Information about the development of a new model perturbation strategy at DWD (0.25 FTEs)
  Ekaterina Machulskaya and Richard Keane (DWD), 01.09.2013 - 31.08.2015
  Deliverable: Good communication to COSMO and timely information, 2 meetings per year at DWD (one during CUS?)

## Slide 6: Task 3. Soil/surface perturbations.
3.1 Study of COSMO model sensitivity to lower boundary initial conditions (0.7 FTEs)
  Nicola Loglisci and Riccardo Bonanno (ARPA Piemonte), Andrzej Mazur and Grzegorz Duniec (IMGW) 01.09.2013 - 31.01.2014
  Deliverable: Sensitivity tests on the behaviour of different COSMO suites to different lower boundary initial conditions. (report)
3.2 Scientific analysis of the possible strategies to be followed: literature review, assessment of more suitable methods (0.3 FTEs)
  Nicola Loglisci and Riccardo Bonanno (ARPA Piemonte), Andrzej Mazur and Grzegorz Duniec (IMGW), Inna Rozinkina and Gdaly Rivin (RHM), 01.09.2013 - 31.03.2014
  Deliverable: Definition of one or more techniques for lower boundary perturbations to be developed for COSMO. (report)

## Slide 7: Task 3. Soil/surface perturbations.
3.3 Develop techniques for lower boundary perturbation (1.4 FTEs)
  3.2.1 test of perturbation of soil model parameters (RHM)
  3.2.2 selection and preparation of algorithms
  3.2.3 setting a test-bed, implementation and testing
  3.2.4 analyse the impact with respect to a non perturbed ensemble
  Nicola Loglisci and Riccardo Bonanno (ARPA Piemonte), Andrzej Mazur, Witold Interewicz and Grzegorz Duniec (IMGW), Inna Rozinkina and Gdaly Rivin (RHM), 28.03.2014 - 31.08.2015
  Deliverable: The algorithm for lower boundary perturbation is implemented in one or more ensemble systems for testing.

## Slide 8: FTEs
FTEs are computed as time completely devoted to the project.
  0.25 FTEs means that for 3 months the person has worked only for the Project (no holidays, no meetings, …)
The COSMO year is from September to August
Reporting (both status of the Project and FTEs) is 3-monthly (SON, DJF, MAM, JJA)
  For SON and MAM reporting is light (FTEs + 1 statement about the status of the project, problems encountered, need of SMC/STC, …)
  For DJF and JJA reporting is heavy (FTEs + (short) written report about the results)

## Slide 9: Coordination
Report to PP coordinator
Meetings:
  web-conferences are asked by STC, possibly monthly, at least 3-monthly
  GM, CUS, other meetings possible (better on a specific Task), depending on the need (COSMO licence money)
It is possible to use COSMO licence money to invite scientists or to visit a scientist within the Project scope
Next meeting (virtual)